## Sheet1
Field | Details
Project Name | OrangeHRM Manual Testing Project
Prepared By | Rohan Malviya
Role | Fresher QA Tester
Testing Type | Manual Testing
Modules Covered | Login Module, Timesheet Module
Tools Used | Excel, Jira
Browser Used | Google Chrome
Defect Report
Defect ID | Project name | Module Name | Phase | Type of defect | Serverity | Priority | Summary | Description | Status
DEF_001 | OrangeHRM | Login Functionality | Testing | Functional Defect | Major | High | ESS User login successful with invalid credentials | According to SRS, ESS User should not login with invalid username/password but system allows access without proper validation message. | New/Open
DEF_002 | OrangeHRM | Forgot Password | Testing | Validation Defect | Medium | Medium | ESS User forgot password accepts invalid username | System accepts invalid ESS username during forgot password process instead of displaying validation message. | New/Open
DEF_003 | OrangeHRM | Timesheet Functionality | Testing | Functional Defect | Major | High | ESS User submitted blank timesheet successfully | According to SRS timesheet entry should require activity/project hours, but ESS User can submit blank timesheet. | New/Open
DEF_004 | OrangeHRM | Timesheet Functionality | Testing | Validation Defect | Major | High | ESS User entered invalid activity hours in timesheet | System accepts negative or invalid hour values entered by ESS User during timesheet entry. | New/Open
DEF_005 | OrangeHRM | Timesheet Functionality | Testing | Functional Defect | Major | High | Supervisor unable to approve employee timesheet | According to SRS Supervisor should approve submitted employee timesheet, but status is not updated after clicking Approve. | New/Open
DEF_006 | OrangeHRM | Timesheet Functionality | Testing | Functional Defect | Major | High | Supervisor unable to reject employee timesheet | Supervisor selects Reject option for employee timesheet but system does not update timesheet status correctly. | New/Open
DEF_007 | OrangeHRM | Timesheet Functionality | Testing | Authorization Defect | Critical | High | ESS User able to approve employee timesheet | ESS User can access approve/reject functionality which according to SRS should only be available to Supervisor/Admin. | New/Open
DEF_008 | OrangeHRM | Timesheet Functionality | Testing | Functional Defect | Medium | Medium | ESS User able to edit submitted timesheet | Submitted timesheet remains editable by ESS User without reset or withdrawal action. | New/Open
DEF_009 | OrangeHRM | Timesheet Functionality | Testing | Functional Defect | Medium | Medium | ESS User reset option not withdrawing approved timesheet | Reset functionality does not revert approved/rejected timesheet status correctly for ESS User. | New/Open
DEF_010 | OrangeHRM | Timesheet Functionality | Testing | Validation Defect | Medium | Medium | Supervisor search accepts invalid employee name | System does not display validation message when Supervisor searches invalid employee name in timesheet module. | New/Open
DEF_011 | OrangeHRM | Print Timesheets | Testing | Functional Defect | Medium | Medium | Supervisor export to CSV downloads empty file | CSV file downloaded by Supervisor contains no timesheet records despite valid report data existing. | New/Open
DEF_012 | OrangeHRM | Print Timesheets | Testing | Validation Defect | Medium | Medium | Supervisor entered invalid date range in print timesheets | System accepts From Date greater than To Date during Supervisor print timesheet operation. | New/Open
DEF_013 | OrangeHRM | Print Timesheets | Testing | Authorization Defect | Critical | High | Supervisor can access non-subordinate employee timesheets | Supervisor can print/view unauthorized employee timesheets outside subordinate access defined in SRS. | New/Open
DEF_014 | OrangeHRM | Attendance | Testing | Functional Defect | Major | High | ESS User allowed Punch Out without Punch In | System allows ESS User to perform Punch Out operation without existing Punch In entry. | New/Open
DEF_015 | OrangeHRM | Attendance | Testing | Validation Defect | Medium | Medium | Supervisor attendance report accepts invalid employee details | Attendance report generates for Supervisor with invalid employee details instead of showing validation message. | New/Open
DEF_016 | OrangeHRM | Attendance Configuration | Testing | Functional Defect | Medium | Medium | Admin attendance configuration changes not saved | Selected attendance configuration privileges by Admin are not saved after clicking Save button. | New/Open
DEF_017 | OrangeHRM | Attendance Configuration | Testing | Validation Defect | Low | Low | Admin save button works without configuration changes | System saves attendance configuration even when Admin makes no changes. | New/Open
DEF_018 | OrangeHRM | Punch In/Out | Testing | Validation Defect | Major | High | ESS User entered invalid time during Punch In | System accepts invalid time values entered by ESS User during Punch In operation. | New/Open
DEF_019 | OrangeHRM | Punch In/Out | Testing | Validation Defect | Major | High | ESS User Punch In successful with blank mandatory fields | System allows ESS User to Punch In without entering mandatory fields. | New/Open
DEF_020 | OrangeHRM | Punch In/Out | Testing | Authorization Defect | Critical | High | Admin able to access restricted Punch In/Out functionality | Admin user can access Punch In/Out functionality which should be role restricted according to SRS. | New/Open
DEF_021 | OrangeHRM | Employee Reports | Testing | Functional Defect | Medium | Medium | Supervisor unable to generate employee attendance report | Supervisor clicks Generate/View but employee attendance report is not displayed for valid inputs. | New/Open
DEF_022 | OrangeHRM | Employee Reports | Testing | Functional Defect | Medium | Medium | Supervisor unable to save updated attendance report | Edited attendance report details by Supervisor are not saved after clicking Save. | New/Open
DEF_023 | OrangeHRM | Employee Reports | Testing | Functional Defect | Medium | Medium | Admin unable to delete multiple employee report entries | System fails to delete multiple selected attendance report entries simultaneously. | New/Open
DEF_024 | OrangeHRM | Employee Reports | Testing | Validation Defect | Medium | Medium | Supervisor report accepts invalid date range | System generates employee attendance report with invalid From and To dates. | New/Open
DEF_025 | OrangeHRM | Project Reports | Testing | Functional Defect | Medium | Medium | Supervisor unable to view project activity details | Clicking View in Project Reports does not open activity detail screen for Supervisor. | New/Open
DEF_026 | OrangeHRM | Project Reports | Testing | Data Defect | Medium | Medium | Incorrect total project hours displayed in Supervisor report | Total project hours calculation does not match employee activity records in Supervisor report. | New/Open
DEF_027 | OrangeHRM | Work Shifts | Testing | Validation Defect | Medium | Medium | Admin created work shift with blank shift name | System allows Admin to add work shift without entering Shift Name. | New/Open
DEF_028 | OrangeHRM | Work Shifts | Testing | Validation Defect | Medium | Medium | Admin entered invalid Hours Per Day in work shift | System accepts negative or zero Hours Per Day values in Work Shift configuration. | New/Open
DEF_029 | OrangeHRM | Work Shifts | Testing | Functional Defect | Medium | Medium | Admin unable to delete multiple work shifts | Delete operation fails for multiple selected work shifts. | New/Open
DEF_030 | OrangeHRM | Work Shifts | Testing | Functional Defect | Major | High | Assigned employee not removed from work shift by Admin | Clicking Remove does not remove employee from assigned employee list in Work Shift module. | New/Open